## Manchal Adm Road
ANNEXURE - B
QUARTERLY PROGRESS REPORT FOR QUARTER ENDING JUNE-2017 PROJECT UNDER NON - LAPSABLE CENTRAL POOL OF RESOURCES SCHEME.
A. Indentification Particulars
1 | Name of Project | : | Construction of road from Hawai District HQ to Manchal Administrative Circle (32.01 Km) in Arunachal Pradesh.Ph-I (SH:-FC & Culverts)
2 | Location |  | Manchal
| State | : | Arunachal Pradesh
| District | : | Anjaw
3 | Approved cost (Rs. In lakh) | : | Rs 3,252.92 Lakhs
4 | Date of approval of Project/Scheme | : | Dtd 08/10/2008
5 | Tender cost (Rs. In lakhs) | : | i)Rs 1,031.76 Lakhs + 328.33 Lakhs deviation=1360.09 Lakhs for 2 to 20km ii) Rs.345 Lakhs through CPWD form-11 iii) NIBapproved for Rs.1335.58 Lakhs for strech 20.00 to 32.01 km
6 | Date of award of contract (copy of work order to be attached (only once for the quarter in which it was issued) | : | 13/03/2009
7 | Whether contract awarded on Turn key basis | : | No, on item rate tender as per MoRTH Standard Biding Documents (SBD)
8 | Whether awarded work in being executed based on PERT/CPM | : | Yes
9 | Original Date of Completion of Project / Scheme | : | 30/11/2010
10 | Re-Schedule Date of Completion of Project / Scheme | : | 31/12/2016 subject to timely release of fund by MDoNER
11 | Executing Agency State Govt./ PSC/ Other agency (specify) | : | Arunachal Pradesh PWD
B. Over all Progress
S/No. | Item | Physical Progress (%) |  |  |  | Total Expenditure incurred (Rs. in lakh)
|  | Beginning of Quarter |  | During Quarter | End of Quarter (Cummulative)
1 | 2 | 3 |  | 4 | 5 | 6
1. | Formation Cutting 32.01 km | 14.73 Km |  | Nil | 14.73 Km | C/S = 1024.67 S/S = 128.13
2. | Slab Culvert 1.50 mtr span 58 Nos | 22 Nos |  | Nil | 22 Nos
3. | Slab Culvert 2.00 mtr span 46 Nos | 29 Nos |  | Nil | 29 Nos |  | 1024.67
4. | Slab Culvert 4.00 mtr span 25 Nos | 10 Nos |  | Nil | 10 Nos |  | 128.13
5 | Slab Culvert 6.00 mtr span 9 Nos | - |  | - | - |  | 1152.8
6 | KM Stone 32.01 km | - |  | - | - |  | 0
| Over all Physical Progress / Total expenditure |  |  |  | 55%
[5 empty] | Total | 1152.8
C. Progress Release of State share
S/No. | Release of funds/payments | Date |  | Amount (Rs. in Lakhs) | Remarks
a | As per AOP 2011-12, fund earmarked Rs. 100.30 Lakhs | 2011-12 |  | 100.3
b | As per AOP 2013-14, fund Rs. 15.00 Lakhs | 2013-14 |  | 15
c | As per AOP 2014-15, fund Rs. 12.83 Lakhs | 2014-15 |  | 12.83
| Total State Released : |  |  | 128.13 Lakhs
| D. No. of Photographs attached :- | Nil
| Sd/- |  |  |  | Sd/-
| Executive Engineer, |  |  |  | Superintending Engineer,
| Hayuliang P.W. Division. |  |  |  | Tezu Circle, PWD, Tezu
| Surveyor of Works | Sr. Finance & Accounts Officer, |  |  | Suptdg. Surveyor of Works O/o Chief Engineer (EZ), Itanagar , Arunachal Pradesh.
| O/o Chief Engineer (EZ), | O/o Chief Engineer (EZ) |  |  | O/o Chief Engineer (EZ)
| PWD, AP,Itanagar. | PWD, AP,Itanagar. |  |  | PWD, AP,Itanagar.
Signature by the Chief Engineer of Implementing Department
| Name : | Kenjom Ete
| Designation : | Chief Engineer, Eastern Zone, PWD, AP, Itanagar
Date :
| Place : | Itanagar
Office seal :

## Anini-Dambuine
ANNEXURE - B
QUARTERLY PROGRESS REPORT FOR QUARTER ENDING SEPTEMBER-2017 PROJECT UNDER NON - LAPSABLE CENTRAL POOL OF RESOURCES SCHEME.
A. Indentification Particulars
1 | Name of Project | : | Constructuon of road from BRO road (4km point) on Anini-Dambuine road to Etabe village( Actual Length 9.50 km in Dibang Valley Distt.
2 | Location
| State | : | Arunachal Pradesh
| District | : | Dibang Valley
3 | Approved cost (Rs. In lakh) | : | 2213.96 Lakhs
4 | Date of approval of Project/Scheme | : | 28/03/2009
5 | Tender cost (Rs. In lakhs) |  | Rs.1302.405/a)Bridge=Rs.979.085 Lakhsb) Pavement= Rs.323.32Lakhs
and other works viz: F/C, Cross Drainage and Protection works
by work order Rs.867.26 lakhs.
6 | Date of award of contract [copy of work order to be attached (only once for the quarter in which it was issued) need not be submitted if submitted in earlier quarter) | : | a) Bridge- June/2010
b) Pavement- March/2012
7 | Whether contract awarded on Turn key basis | : | No
8 | Whether awarded work in being executed based on PERT/CPM | : | Yes
9 | Original Date of Completion of Project / Scheme | : | March '2013
10 | Re-Schedule Date of Completion of Project / Scheme | : | December '2017
11 | Executing Agency State Govt./ PSC/ Other agency (specify) | : | Arunachal Pradesh PWD
B. Over all Progress
S/No. | Item | Physical Progress (%) |  |  |  | Total Expenditure incurred (Rs. in lakh)
|  | Beginning of Quarter |  | During Quarter | End of Quarter (Cummulative)
1 | 2 | 3 |  | 4 | 5 | 6
1 | Formation Cutting | 9.00km. |  | Nil | 9.00 km | C/S = 989.89 S/S =172.40
2 | Cross Drainage work
| a)RCC Slab Culvert 1.50 Mtr span (15 Nos.) | 15 Nos. |  | Nil | 15.00 Nos
| b)RCC Slab Culvert 2.00 Mtr span (30 Nos.) | 30 Nos. |  | Nil | 30 Nos
| c)RCC Slab Culvert 3.00 Mtr span (6 Nos.) | 2 Nos |  | Nil | 2 Nos
| d)RCC Slab Culvert 6.00 Mtr span (4 Nos.) | - |  | - | -
3 | Protection Works
| a)Retaining wall 3 mtr. Ht.(703.00 mtr.) | 721.70mtr |  | Nil | 721.70 mtr
| b)Breast wall 3 mtr. Ht.(297.00 mtr.) | 319.40 mtr |  | Nil | 319.40 mtr
4 | Kutcha Drain (9.237 km.) | 6000.00 mtr. |  | Nil | 6000.00 mtr.
5 | Pavement
| a)Sub-base coarse (9.237 km.) | 7.80 km. |  | Nil | 7.80 km
| b)Base coarse WBM II (9.237 km.) | 6.10 km. |  | Nil | 6.10 km
| c)Base coarse WBM III (9.237 km.) | 6.10 km. |  | Nil | 6.10 km
| d)Premixed carpetting& seal coat (9.237 km.) | 6.10 km. |  | Nil | 6.10 km
6 | C/o Steel Suspension Bridge
| Span-138.00 mtr. | i) Right bank abutment 100% completed ii)Left bank abutment 100% completed |  | - | Both Side abutment completed
7 | Contigencies @2%
| Over all Physical Progress / Total expenditure | 65% |  |  |  | 1162.29
C. Progress Release of State share
S/No. | Release of funds/payments | Date |  | Amount (Rs. in Lakhs) |  | Remarks
| Cetral Share | 2009-2010 |  | 697.4 |  | 1562.15
| Cetral Share | 2015-2016 |  | 864.75
b | State Govt. to concern department | 2011-2012 |  | 60 |  | 80.4
| State Govt. to concern department | 2011-2012 |  | 20.4
| State Govt. to concern department | 2015-2016 |  | 92 |  | 92
| Total State Release : |  |  | 172.4 |  | 1734.55
| D. No. of Photographs attached :- | Nil
| Sd/- |  |  |  | Sd/-
| Executive Engineer, |  |  |  | Superintending Engineer,
| Anini P.W. Division. |  |  |  | Tezu Circle, PWD, Tezu
| Surveyor of Works | Sr. Finance & Accounts Officer, |  |  | Suptdg. Surveyor of Works O/o Chief Engineer (EZ), Itanagar , Arunachal Pradesh.
| O/o Chief Engineer (EZ), | O/o Chief Engineer (EZ) |  |  | O/o Chief Engineer (EZ)
| PWD, AP,Itanagar. | PWD, AP,Itanagar. |  |  | PWD, AP,Itanagar.
Signature by the Chief Engineer of Implementing Department
| Name : | Kenjom Ete
| Designation : | Chief Engineer, Eastern Zone, PWD, AP, Itanagar
Date :
| Place : | Itanagar
Office seal :

## Jia Tinali
ANNEXURE - B
QUARTERLY PROGRESS REPORT FOR QUARTER ENDING SEPTEMBER-2017 PROJECT UNDER NON - LAPSABLE CENTRAL POOL OF RESOURCES SCHEME.
A. Indentification Particulars
1 | Name of Project | : | C/O of Road from Jia Tinali on Roing Shantipur road (9.20km) to Bijari via Idilli (19.80 km) in Arunachal Pradesh.
2 | Location
| State | : | Arunachal Pradesh
| District | : | Lower Dibang Valley
3 | Approved cost (Rs. In lakh) | : | Rs.1544.61 Lakhs
4 | Date of approval of Project/Scheme | : | DNER/NLP/AP/122/2008 Dtd.05.02.2010
5 | Tender cost (Rs. In lakhs) | : | Rs.845.94 Lakhs
6 | Date of award of contract [copy of work order to be attached (only once for the quarter in which it was issued) need not be submitted if submitted in earlier quarter) | : | 20.01.2012
7 | Whether contract awarded on Turn key basis | : | No.On item Rate Contract.
8 | Whether awarded work in being executed based on PERT/CPM | : | Yes
9 | Original Date of Completion of Project / Scheme | : | 19.04.2014
10 | Re-Schedule Date of Completion of Project / Scheme | : | March'2016
11 | Executing Agency State Govt./ PSC/ Other agency (specify) | : | Arunachal Pradesh PWD
B. Over all Progress
S/No. | Item | Physical Progress (%) |  |  |  | Total Expenditure incurred (Rs. in lakh
|  | Beginning of Quarter |  | During Quarter | End of Quarter (Cummulative)
1 | 2 | 3 |  | 4 | 5 | 6
I. | Jungle clearance -36.44 hact. | 18.900 km (36.44 hact.) |  | Nil | 18.900 km(36.44 hact.) | C/S=1090.30 S/S=120.00
II. | Earthwork
| (a) Formation cutting -273087.85cum | 18.900km (273087.85 cum) |  | Nil | 18.900 km(273087.85 cum)
III. | Protection works
| Boulder crated walls 5091.00 cum (950 mtr) | 270.00 mtr. |  | Nil | 270.00 mtr.
IV. | SH:- Soling, Metalling, carpeting.
| (a) Earthen shoulder 14.90 km (2976.75 cum) | 0.400 km |  | Nil | 0.400 km
| (b) WBM -with grade I -14.9 km(8234.74 cum) | 2.746 km(1527.91 Cum) |  | Nil | 2.746 km(1527.91 Cum)
| (c) WBM - with grade II- 18.9 km(7313.87 cum) | 6.746 km (2610.54 Cum) |  | Nil | 6.746 km (2610.54 Cum) |  | 1090.3
| (d) WBM - with grade III -18.9 km(6772.101 cum) | 6.746 km (2417.17 Cum) |  | Nil | 6.746 km (2417.17 Cum) |  | 120
| (e) Carpeting -18.9 km(74418.75 sqm ) | 6.746 km (26562.38 Sqm) |  | Nil | 6.746 km (26562.38 Sqm) |  | 1210.3
V. | Culverts
| (a) 1 mtr span - 11 Nos. | 4 Nos. |  | Nil | 4 Nos.
| (b) 2 mtr span - 6 Nos. | 6 Nos. |  | Nil | 6 Nos.
| (c) 4 mtr span - 9 Nos. | 8 Nos. |  | Nil | 8 Nos.
| (d) 6 mtr span -8Nos. | 4 Nos. |  | Nil | 4 Nos.
VI | Contigencies.
| Over all Physical Progress / Total expenditure |  |  |  | 70% | 1210.3
C. Progress Release of State share
S/No. | Release of funds/payments | Date |  | Amount (Rs. in Lakhs) |  | Remarks
b | State Govt. to concern department |  |  | Nil
| Total State Released : |  |  | Nil
| D. No. of Photographs attached :- | Nil
| Sd/- |  |  |  | Sd/-
| Executive Engineer, |  |  |  | Superintending Engineer,
| Roing P.W. Division. |  |  |  | Tezu Circle, PWD, Tezu
| Surveyor of Works | Sr. Finance & Accounts Officer, |  |  | Suptdg. Surveyor of Works O/o Chief Engineer (EZ), Itanagar , Arunachal Pradesh.
| O/o Chief Engineer (EZ), | O/o Chief Engineer (EZ) |  |  | O/o Chief Engineer (EZ)
| PWD, AP,Itanagar. | PWD, AP,Itanagar. |  |  | PWD, AP,Itanagar.
Signature by the Chief Engineer of Implementing Department
| Name : | Kenjom Ete
| Designation : | Chief Engineer, Eastern Zone, PWD, AP, Itanagar
Date :
| Place : | Itanagar
Office seal :

## NH-153 LT
ANNEXURE - B
QUARTERLY PROGRESS REPORT FOR QUARTER ENDING SEPTEMBER-2017 PROJECT UNDER NON - LAPSABLE CENTRAL POOL OF RESOURCES SCHEME.
A. Indentification Particulars
1 | Name of Project | : | Construction of road from NH-153 Longvi village point to Tengman village via Khetwa & Jotin Juda village (35.00 Km) in Changlang District .
2 | Location
| State | : | Arunachal Pradesh
| District | : | Changlang
3 | Approved cost (Rs. In lakh) | : | 2133.60 Lakhs
4 | Date of approval of Project/Scheme | : | DNER/NLP/AP/151/2010 Dtd 28.02.2011
5 | Tender cost (Rs. In lakhs) | : | 1,951.51 Lakhs
6 | Date of award of contract (copy of work order to be attached (only once for the quarter in which it was issued) | : | 28/02/2011
7 | Whether contract awarded on Turn key basis | : | No
8 | Whether awarded work in being executed based on PERT/CPM | : | Yes
9 | Original Date of Completion of Project / Scheme | : | 28/02/2014 (36 months)
10 | Re-Schedule Date of Completion of Project / Scheme | : | 31/03/2017(as per contract agreement & subject to availability of fund in time)
11 | Executing Agency State Govt./ PSC/ Other agency (specify) | : | Arunachal Pradesh PWD
B. Over all Progress
S/No. | Item | Physical Progress (%) |  |  |  | Total Expenditure incurred (Rs. in lakh
|  | Beginning of Quarter |  | During Quarter | End of Quarter (Cummulative)
1 | 2 | 3 |  | 4 | 5 | 6
1 | S&I - 35.00 Km | 35.00 km |  | Nil | 35.00 km | C/S=1756.36 S/S=193.57
2 | Formation Cutting - 34.703 Km | 34.703 Km |  | Nil | 34.703 Km
3. | CD Works
| i) RCC S/Culvert (1 mtr span) - 52 No(31 Nos Revised Scope) | 17 Nos. |  | Nil | 17 Nos.
| ii) RCC S/Culvert (2 mtr span) - 75 Nos (67 Nos Revised Scope) | 66Nos. |  | Nil | 66Nos.
| iii) RCC S/Culvert (4 mtr span) - 8 Nos | 6 Nos. |  | Nil | 6 Nos.
| iv) RCC S/Culvert (6 mtr span) - 3 Nos | 2 Nos. |  | Nil | 2 Nos.
4. | Katcha Drain - 34.703 Km | 34.700 Km. |  | Nil | 34.700 Km.
5. | RCC Bridge (30 mtr span) - 1 No | Abutment completed. |  | - | Abutment completed.
| Over all Physical Progress / Total expenditure |  |  |  | 95% | 1949.93
C. Progress Release of State share
S/No. | Release of funds/payments | Date |  | Amount | Remarks
a | Central Share |  |  | 1756.36
b | State Share |  |  | 193.57
| Total State Released : |  |  | 1949.93
| D. No. of Photographs attached :- | Nil
| Sd/- |  |  |  | Sd/-
| Executive Engineer, |  |  |  | Superintending Engineer,
| Jairampur P.W. Division. |  |  |  | Jairampur Circle, PWD, Jairampur
| Surveyor of Works | Sr. Finance & Accounts Officer, |  |  | Suptdg. Surveyor of Works O/o Chief Engineer (EZ), Itanagar , Arunachal Pradesh.
| O/o Chief Engineer (EZ), | O/o Chief Engineer (EZ) |  |  | O/o Chief Engineer (EZ)
| PWD, AP,Itanagar. | PWD, AP,Itanagar. |  |  | PWD, AP,Itanagar.
Signature by the Chief Engineer of Implementing Department
| Name : | Kenjom Ete
| Designation : | Chief Engineer, Eastern Zone, PWD, AP, Itanagar
Date :
| Place : | Itanagar
Office seal :

## NM-Mpen rd
ANNEXURE - B
QUARTERLY PROGRESS REPORT FOR QUARTER ENDING SEPTEMBER-2017 PROJECT UNDER NON - LAPSABLE CENTRAL POOL OF RESOURCES SCHEME.
A. Indentification Particulars
1 | Name of Project | : | Upgrdation of Namchik Miao-M'pen road 37 Km.(Phase-1)for new construction only in Changlang District.(0.00km to 26.50 km.)
2 | Location
| State | : | Arunachal Pradesh
| District | : | Changlang
3 | Approved cost (Rs. In lakh) | : | 2079.84 Lakhs
4 | Date of approval of Project/Scheme | : | DNER/NLP/AP/120/2008 Dtd 19.09.2011
5 | Tender cost (Rs. In lakhs) | : | 1,925.13 Lakhs
6 | Date of award of contract (copy of work order to be attached (only once for the quarter in which it was issued) | : | 13/02/2013
7 | Whether contract awarded on Turn key basis | : | No
8 | Whether awarded work in being executed based on PERT/CPM | : | Yes
9 | Original Date of Completion of Project / Scheme | : | 31/03/2014(36 months)
10 | Re-Schedule Date of Completion of Project / Scheme | : | 31/03/2017 (as per contract agreement & subject to availability of fund in time)
11 | Executing Agency State Govt./ PSC/ Other agency (specify) | : | Arunachal Pradesh PWD
B. Over all Progress
S/No. | Item | Physical Progress (%) |  |  |  | Total Expenditure incurred (Rs. in lakh
|  | Beginning of Quarter | During Quarter | End of Quarter (Cummulative)
1 | 2 | 3 | 4 | 5 |  | 6
1 | Jungle clearance 26.50 km. | 26.50km. | - | 26.50km.
2 | Formation Cutting - 26.19 Km | 26.19km. | - | 26.19km.
3. | CD Works
| i) RCC S/Culvert (1 mtr span) - 7 Nos | 6Nos. | 1No. | 7Nos.
Extension of
| ii) RCC S/Culvert (4 mtr span) - 10 Nos | 10Nos. | - | 10Nos.
| iii) RCC S/Culvert (6 mtr span) - 10 Nos | 10Nos. | - | 10Nos. |  | C/S=1554.50 S/S=207.99
iv) Km Stone & Road sign
4. | Pavement
| i) Soling (GSB - Grd-I) - 26.190 Km | 26.190 km | - | 26.190 km
| ii) WBM - 26.190 Km | 26.190 km | - | 26.190 km
| iii) BT (PC & SC) - 26.190 Km | 24.850 km. | 1.340Km | 26.190 km.
5. | Shifting of utilities | - | - | -
6. | Contigencies
| Over all Physical Progress / Total expenditure |  |  | 100% |  | 1762.49
C. Progress Release of State share
S/No. | Release of funds/payments | Date |  | Amount | Remarks
a | Central share |  |  | 1732.62
b | State Share | 18/01/2016 |  | 207.99
| Total Funds Released : |  |  | 1940.61
| D. No. of Photographs attached :- | 4Nos.
| Sd/- |  |  |  | Sd/-
| Executive Engineer, |  |  |  | Superintending Engineer,
| Jairampur P.W. Division. |  |  |  | Jairampur Circle, PWD, Jairampur
| Surveyor of Works | Sr. Finance & Accounts Officer, |  | Suptdg. Surveyor of Works O/o Chief Engineer (EZ), Itanagar , Arunachal Pradesh.
| O/o Chief Engineer (EZ), | O/o Chief Engineer (EZ) |  | O/o Chief Engineer (EZ)
| PWD, AP,Itanagar. | PWD, AP,Itanagar. |  | PWD, AP,Itanagar.
Signature by the Chief Engineer of Implementing Department
| Name : | Kenjom Ete
| Designation : | Chief Engineer, Eastern Zone, PWD, AP, Itanagar
Date :
| Place : | Itanagar
Office seal :

## vkv changlang
ANNEXURE - B
QUARTERLY PROGRESS REPORT FOR QUARTER ENDING SEPTEMBER-2017 PROJECT UNDER NON - LAPSABLE CENTRAL POOL OF RESOURCES SCHEME.
A. Indentification Particulars
1 | Name of Project | : | Establishment of V.K.V at Changlang in Changlang District.
2 | Location
| State | : | Arunachal Pradesh
| District | : | Changlang
3 | Approved cost (Rs. In lakh) | : | 501.55 Lakhs
4 | Date of approval of Project/Scheme | : | 23/09/2011
5 | Tender cost (Rs. In lakhs) | : | 490.95Lakhs
6 | Date of award of contract [copy of work order to be attached (only once for the quarter in which it was issued) need not be submitted if submitted in earlier quarter) | : | 29-04-2013
7 | Whether contract awarded on Turn key basis | : | Yes
8 | Whether awarded work in being executed based on PERT/CPM | :
9 | Original Date of Completion of Project / Scheme | : | 28.04.2015
10 | Re-Schedule Date of Completion of Project / Scheme | : | 31.03.2016
11 | Executing Agency State Govt./ PSC/ Other agency (specify) | : | Arunachal Pradesh PWD
B. Over all Progress
S/No. | Item | Physical Progress (%) |  |  |  | Total Expenditure incurred (Rs. in lakh
|  | Beginning of Quarter |  | During Quarter | End of Quarter (Cummulative)
1 | 2 | 3 |  | 4 | 5 | 6
1 | Jungle clearance - 25500 Sqm | 100% completed |  | - | 100% completed | C/S=177.55 S/S=17.76
2 | School Bldg (G+1) 1834.58 Sqm | Nil |  | Nil | Nil
3 | Hostel Bldg - 2 Blocks of 40 boarders (G +2) 1399.32 Sqm | Both block completed , Except flooring doors, windows, grils,railing, sanitary,water supply & finishing. |  | Nil | Both block completed , Except flooring doors, windows, grils,railing, sanitary,water supply & finishing.
4 | Site development 17437.78 km | 100% completed |  | Nil | 100% completed |  | 177.55
5 | Formation Cutting 990 mtr | 100% completed |  | Nil | 100% completed |  | 17.76
6 | Surface drain 990 mtr | 450.00 mtr |  | Nil | 450.00 mtr |  | 195.31
7 | Sub Base course 990 mtr | 200.00 mtr |  | Nil | 200.00 mtr
8 | Residential Building( T-I: 2 Nos, T-II: 2 Nos) | T-II 2 Nos completed G/Floor up to L/Level & T I 2 Nos. up to plinth level |  | Nil | T-II 2 Nos completed G/Floor up to L/Level & T I 2 Nos. up to plinth level
| Over all Physical Progress / Total expenditure |  |  |  | 45% | 195.31
C. Progress Release of State share
S/No. | Release of funds/payments | Date |  | Amount (Rs. in Lakhs) |  | Remarks
b | State Govt. to concern department |  |  | 17.76
| Total State Released : | 2015-16 |  | 17.76
| D. No. of Photographs attached :- | Nil
| Sd/- |  |  |  | Sd/-
| Executive Engineer, |  |  |  | Superintending Engineer,
| Changlang P.W. Division. |  |  |  | Jairampur Circle, PWD, Jairampur
| Surveyor of Works | Sr. Finance & Accounts Officer, |  |  | Suptdg. Surveyor of Works O/o Chief Engineer (EZ), Itanagar , Arunachal Pradesh.
| O/o Chief Engineer (EZ), | O/o Chief Engineer (EZ) |  |  | O/o Chief Engineer (EZ)
| PWD, AP,Itanagar. | PWD, AP,Itanagar. |  |  | PWD, AP,Itanagar.
Signature by the Chief Engineer of Implementing Department
| Name : | Kenjom Ete
| Designation : | Chief Engineer, Eastern Zone, PWD, AP, Itanagar
Date :
| Place : | Itanagar
Office seal :

## GHS Hawai
ANNEXURE - B
QUARTERLY PROGRESS REPORT FOR QUARTER ENDING SEPTEMBER-2017 PROJECT UNDER NON - LAPSABLE CENTRAL POOL OF RESOURCES SCHEME.
A. Indentification Particulars
1 | Name of Project | : | Infrastructure Development of Govt.Higher Secondary School Hawai (C/o School Building Only) in Anjaw Dist .
2 | Location |  | Hawai
| State | : | Arunachal Pradesh
| District | : | Anjaw
3 | Approved cost (Rs. In lakh) | : | C/S=Rs 975.52 Lakhs, S/S=Rs 108.39 Lakhs Total Rs.1083.91 Lakhs
4 | Date of approval of Project/Scheme | : | 19/12/2012
5 | Tender cost (Rs. In lakhs) | : | 999.42 lakhs
6 | Date of award of contract (copy of work order to be attached (only once for the quarter in which it was issued) | : | 19/09/2013
7 | Whether contract awarded on Turn key basis | : | Work awarded on TurnKey basis to M/S G.P.Enterprises,Vill. Lautul,PO.Hawai,Dist.Anjaw,AP.
8 | Whether awarded work in being executed based on PERT/CPM | : | Yes
9 | Original Date of Completion of Project / Scheme | : | July'2016
10 | Re-Schedule Date of Completion of Project / Scheme | : | -
11 | Executing Agency State Govt./ PSC/ Other agency (specify) | : | Arunachal Pradesh PWD
B. Over all Progress
S/No. | Item | Physical Progress (%) |  |  |  | Total Expenditure incurred (Rs. in lakh
|  | Beginning of Quarter |  | During Quarter | End of Quarter (Cummulative)
1 | 2 | 3 |  | 4 | 5 | 6
1. | School Building | Building F/F complted & F/F truss work in progress |  | F/F truss work ,CGI sheet fixing and wall work in progress | Building F/F complted upto roof level & F/F truss work CGI sheet fixing and wall work in progress | C/S=390.20 S/S=71.96 | 390.2
71.96
462.16
| Over all Physical Progress / Total expenditure |  |  |  | 70% | 462.16
C. Progress Release of State share
S/No. | Release of funds/payments | Date |  | Amount (Rs. in Lakhs) | Remarks
a | Central Share | - |  | 390.2
| State Share | 2016-17 |  | 71.96
| Total |  |  | 462.16
| D. No. of Photographs attached :- | 2 Nos.
| Sd/- | Sd/-
| Executive Engineer, | Superintending Engineer,
| Hayuliang P.W. Division. | Tezu Circle, PWD, Tezu
| Surveyor of Works | Sr. Finance & Accounts Officer, |  |  | Suptdg. Surveyor of Works O/o Chief Engineer (EZ), Itanagar , Arunachal Pradesh.
| O/o Chief Engineer (EZ), | O/o Chief Engineer (EZ) |  |  | O/o Chief Engineer (EZ)
| PWD, AP,Itanagar. | PWD, AP,Itanagar. |  |  | PWD, AP,Itanagar.
Signature by the Chief Engineer of Implementing Department
| Name : | Kenjom Ete
| Designation : | Chief Engineer, Eastern Zone, PWD, AP, Itanagar
Date :
| Place : | Itanagar
Office seal :

## HA to Echigo
ANNEXURE - B
QUARTERLY PROGRESS REPORT FOR QUARTER ENDING SEPTEMBER-2017 PROJECT UNDER NON - LAPSABLE CENTRAL POOL OF RESOURCES SCHEME.
A. Indentification Particulars
1 | Name of Project | : | C/O road from 168 Km point to Roing- Anini BRTF road to Echigo village in Dibang Valley (12 Km) District , Arunachal Pradesh.
2 | Location
| State | : | Arunachal Pradesh
| District | : | Dibang Valley District.
3 | Approved cost (Rs. In lakh) | : | Rs.1861.21 Lakhs
4 | Date of approval of Project/Scheme | : | 19.09.2013
5 | Tender cost (Rs. In lakhs) | : | Rs.1751.13 Lakhs
6 | Date of award of contract | : | 14/11/2014
7 | Whether contract awarded on Turn key basis | : | No.
8 | Whether awarded work in being executed based on PERT/CPM | : | Yes
9 | Original Date of Completion of Project / Scheme | : | 2017-04-06
10 | Re-Schedule Date of Completion of Project / Scheme | : | -
11 | Executing Agency State Govt./ PSC/ Other agency (specify) | : | Arunachal Pradesh PWD
B. Over all Progress
S/No. | Item | Physical Progress (%) |  |  |  | Total Expenditure incurred (Rs. in lakh
|  | Beginning of Quarter |  | During Quarter | End of Quarter (Cummulative)
1 | 2 | 3 |  | 4 | 5 | 6
1 | Jungle Clearance (12.000 Km) | 12.00 km |  | Nil | 12.00 km. | C/S=670.03 S/S=36.25
2 | Formation cutting -(11.880 Km) | 9.000 km |  | 0.280 km | 9.280 km.
3 | Cross drainage works.
| a)Rcc Slab Culvert 1.50 mtr span (41 Nos) | 21 Nos |  | Nil | 21 Nos.
| b)Rcc Slab Culvert 2.00 mtr span (13 Nos) | 8 Nos |  | Nil | 8 Nos
| c)Rcc Slab Culvert 3.00 mtr span (3 Nos) | - |  | Nil | -
| d)Rcc Slab Culvert 6.00 mtr span (4 Nos) | - |  | Nil | -
4 | Protection works
| a)Retaining wall -3 m height (440.00 mtr) | 221 mtr |  | Nil | 221 mtr
| b)Breast wall -3 m height (200.00 mtr) | 83.00 mtr |  | Nil | 83.00 mtrs.
5 | Pavement
| a. GSB 11.880Km | 1.500 km |  | Nil | 1.500 km
| b. WBM-II- 11.880 Km | - |  | Nil | -
| c. WBM-III- 11.880 Km | - |  | Nil | -
| d.Carpetting 11.880 Km | - |  | Nil | -
6 | Katcha Drain-11.880Km | 1.32 km. |  | Nil | 1.32 km
7 | Road Furniture=12.000km. | Nil |  | Nil | Nil
| Over all Physical Progress / Total expenditure |  |  |  | 43% | 706.28
C. Progress Release of State share
S/No. | Release of funds/payments | Date |  | Amount (Rs. in Lakhs) |  | Remarks
a | Central Share (1st phase) | 2013-14 |  | 1260.81 | 670.03
b | State Govt. to concern department | 2016-17 |  | 36.25
| Total Expenditure : |  |  | 1297.06
| D. No. of Photographs attached :- | Nil
| Sd/- |  |  |  | Sd/-
| Executive Engineer, |  |  |  | Superintending Engineer,
| Anini P.W. Division. |  |  |  | Tezu Circle, PWD, Tezu
| Surveyor of Works | Sr. Finance & Accounts Officer, |  |  | Suptdg. Surveyor of Works O/o Chief Engineer (EZ), Itanagar , Arunachal Pradesh.
| O/o Chief Engineer (EZ), | O/o Chief Engineer (EZ) |  |  | O/o Chief Engineer (EZ)
| PWD, AP,Itanagar. | PWD, AP,Itanagar. |  |  | PWD, AP,Itanagar.
Signature by the Chief Engineer of Implementing Department
| Name : | Kenjom Ete
| Designation : | Chief Engineer, Eastern Zone, PWD, AP, Itanagar
Date :
| Place : | Itanagar
Office seal :

## Changlang-Khimiyang
ANNEXURE - B
QUARTERLY PROGRESS REPORT FOR QUARTER ENDING SEPTEMBER-2017 PROJECT UNDER NON - LAPSABLE CENTRAL POOL OF RESOURCES SCHEME.
A. Indentification Particulars
1 | Name of Project | : | Strengthening and Improvement of Changlang to Khimiyang Road Ph-II (0.00 to 14.500 km.) in Changlang District.
2 | Location
| State | : | Arunachal Pradesh
| District | : | Changlang
3 | Approved cost (Rs. In lakh) | : | Rs 693.40 Lakhs
4 | Date of approval of Project/Scheme | : | Dtd 24/10/2013
5 | Tender cost (Rs. In lakhs) | : | Rs. 673.36 Lakhs.
6 | Date of award of contract (copy of work order to be attached (only once for the quarter in which it was issued) | : | Not yet awarded (financial bidding in progress)
7 | Whether contract awarded on Turn key basis | : | No.
8 | Whether awarded work in being executed based on PERT/CPM | : | Work not yet awarded
9 | Original Date of Completion of Project / Scheme | : | 31/03/2016
10 | Re-Schedule Date of Completion of Project / Scheme | : | -
11 | Executing Agency State Govt./ PSC/ Other agency (specify) | : | Arunachal Pradesh PWD |  |  |  |  | `
B. Over all Progress
S/No. | Item | Physical Progress (%) |  |  |  | Total Expenditure incurred (Rs. in lakh
|  | Beginning of Quarter |  | During Quarter | End of Quarter (Cummulative)
1 | 2 | 3 |  | 4 | 5 | 6
1. | Restoration of rain cuts-14.439 km. | 14.50 Km |  | Nil | 14.50 Km | C/S=249.62 S/S=25.00 | 14.439 | 14.5 | 1.0042 | 100 | 100.4225
2 | WBM-II-14.439 Km | 11.60 km. |  | Nil | 11.60 km. |  | 14.439 | 11.7 | 0.81031 | 100 | 81.0305
3 | WBM-III-14.439 Km | 11.49 Km |  | Nil | 11.49 Km |  | 14.439 | 11.49 | 0.79576 | 100 | 79.5761
4 | B/T and seal coat 14.439 Km | Nil |  | Nil | Nil |  | 14.439 |  | 0 | 100 | 0
5 | C.C.Drain 14.439 Km | 6.50 Km |  | Nil | 6.50 Km |  | 14.439 | 6.5 | 0.45017 | 100 | 45.017
6 | W' Beam Crash Barrier 3400 mtrs. | Nil |  | Nil | Nil | [5 empty] | 306.0461
7 | RCC Km. Stone -15 Nos. | Nil |  | Nil | Nil
8 | Road signboard & Road Signal-15 Nos (13.50 Sqm.) | Nil |  | Nil | Nil
| Over all Physical Progress / Total expenditure |  |  |  | 40% | 274.62 |  |  |  | 77%
C. Progress Release of State share
S/No. | Release of funds/payments | Date |  | Amount (Rs. in Lakhs) | Remarks
| Central Share |  |  | 249.62
| State Share | 2016-17 |  | 25
| Total Expenditure: |  |  | 274.62
| D. No. of Photographs attached :- | Nil
| Sd/- |  |  |  | Sd/-
| Executive Engineer, |  |  |  | Superintending Engineer,
| Changlang P.W. Division. |  |  |  | Jairampur Circle, PWD, Tezu
| Surveyor of Works | Sr. Finance & Accounts Officer, |  |  | Suptdg. Surveyor of Works O/o Chief Engineer (EZ), Itanagar , Arunachal Pradesh.
| O/o Chief Engineer (EZ), | O/o Chief Engineer (EZ) |  |  | O/o Chief Engineer (EZ)
| PWD, AP,Itanagar. | PWD, AP,Itanagar. |  |  | PWD, AP,Itanagar.
Signature by the Chief Engineer of Implementing Department
| Name : | Kenjom Ete
| Designation : | Chief Engineer, Eastern Zone, PWD, AP, Itanagar
Date :
| Place : | Itanagar
Office seal :

## Manchal Adm Bridge
ANNEXURE - B
QUARTERLY PROGRESS REPORT FOR QUARTER ENDING SEPTEMBER-2017 PROJECT UNDER NON - LAPSABLE CENTRAL POOL OF RESOURCES SCHEME.
A. Indentification Particulars
1 | Name of Project | : | Construction of road from Hawai District HQ to Manchal Administrative Circle (32.01 Km) phased-II of Anjaw Distt. in Arunachal Pradesh (SH:-Pmt.Bridges).
2 | Location |  | Manchal
| State | : | Arunachal Pradesh
| District | : | Anjaw
3 | Approved cost (Rs. In lakh) | : | Rs 3331.33 Lakhs
4 | Date of approval of Project/Scheme | : | Dtd 19/12/2013
5 | Tender cost (Rs. In lakhs) | : | i)Rs 971.43 Lakhs for 5 Nos. of bridges
6 | Date of award of contract | : | 10/12/2014
7 | Whether contract awarded on Turn key basis | : | Yes,on turnkey basis
8 | Whether awarded work in being executed based on PERT/CPM | : | Yes
9 | Original Date of Completion of Project / Scheme | : | 09/06 2017
10 | Re-Schedule Date of Completion of Project / Scheme | : | 31/12/2016
11 | Executing Agency State Govt./ PSC/ Other agency (specify) | : | Arunachal Pradesh PWD
B. Over all Progress
S/No. | Item | Physical Progress (%) |  |  |  | Total Expenditure incurred (Rs. in lakh
|  | Beginning of Quarter |  | During Quarter | End of Quarter (Cummulative)
1 | 2 | 3 |  | 4 | 5 | 6
1 | RCC. Pmt.Bridge 15.00 mtr span- 3 Nos.(Now 10.00 Mtr) | 1) 10 m (Ch:- 2.40 Km.) Abutment 2 Nos completed 2) 10mtr (CH 6.80 km) up to Deck slab except approach road river training work 3) 15mtr (CH-11.50 km) completed except approach road 4)10 M (Ch:-11.72 km.) upto Deck slab except approach road river training work |  | 1) 10 m (Ch:- 2.40 Km.) Abutment 2 nos 2) 10 m (Ch:- 6.80 Km.)Bridge completed 3) 15mtr (CH-11.50 km) Bridge completed 4)10 M (11.72 km.) Bridge completed | 1) 10 m (Ch:- 2.40 Km.) Abutment 2 nos 2) 10 m (Ch:- 6.80 Km.)Bridge completed 3) 15mtr (CH-11.50 km) Bridge completed 4)10 M (11.72 km.) Bridge completed | 1199.28
2 | RCC. Pmt.Bridge 10 mtr span- 1No.
3. | RCC. Pmt.Bridge 45 mtr span 1No. | - |  | - | -
| Over all Physical Progress / Total expenditure |  |  |  | 85% | 1199.28
C. Progress Release of State share
S/No. | Release of funds/payments | Date |  | Amount (Rs. in Lakhs) | Remarks
a | Central share |  |  | 1199.28
b | State Share |  |  | 119.93
| Total Fund Released : | - |  | 1319.21 | -
| D. No. of Photographs attached :- | 4 Nos.
| Sd/- |  |  |  | Sd/-
| Executive Engineer, |  |  |  | Superintending Engineer,
| Hayuliang P.W. Division. |  |  |  | Tezu Circle, PWD, Tezu
| Surveyor of Works | Sr. Finance & Accounts Officer, |  |  | Suptdg. Surveyor of Works O/o Chief Engineer (EZ), Itanagar , Arunachal Pradesh.
| O/o Chief Engineer (EZ), | O/o Chief Engineer (EZ) |  |  | O/o Chief Engineer (EZ)
| PWD, AP,Itanagar. | PWD, AP,Itanagar. |  |  | PWD, AP,Itanagar.
Signature by the Chief Engineer of Implementing Department
| Name : | Kenjom Ete
| Designation : | Chief Engineer, Eastern Zone, PWD, AP, Itanagar
Date :
| Place : | Itanagar
Office seal :

## Road from Kanubari to Bogapani
ANNEXURE - B
QUARTERLY PROGRESS REPORT FOR QUARTER ENDING SEPTEMBER-2017 PROJECT UNDER NON - LAPSABLE CENTRAL POOL OF RESOURCES SCHEME.
A. Indentification Particulars
1 | Name of Project | : | Construction of Road from Kanubari to Bogapani via Ranglua and Lawnu CO. HQ (41.00 Km.)Ph-1
2 | Location
| State | : | Arunachal Pradesh
| District | : | Longding.
3 | Approved cost (Rs. In lakh) | : | Rs 2069.00 Lakhs
4 | Date of approval of Project/Scheme | : | Dtd 20/02/2014
5 | Tender cost (Rs. In lakhs) | : | Rs. 2068.65 Lakhs.
6 | Date of award of contract (copy of work order to be attached (only once for the quarter in which it was issued) | : | 29/01/2015 NA.
7 | Whether contract awarded on Turn key basis | : | This work is being executive through Tender/Agreement.
8 | Whether awarded work in being executed based on PERT/CPM | : | NA.
9 | Original Date of Completion of Project / Scheme | : | July 2017
10 | Re-Schedule Date of Completion of Project / Scheme | : | NA.
11 | Executing Agency State Govt./ PSC/ Other agency (specify) | : | Arunachal Pradesh PWD
B. Over all Progress
S/No. | Item | Physical Progress (%) |  |  |  | Total Expenditure incurred (Rs. in lakh
|  | Beginning of Quarter |  | During Quarter | End of Quarter (Cummulative)
1 | 2 | 3 |  | 4 | 5 | 6
1. | F/C - 7.00 Km | 7km. |  | - | 7km. | C/S=989.70 S/S=150.00 | 7 | 7 | 1 | 100 | 100
2 | Widening - 7.19 Km. | 7.19km. |  | - | 7.19km. |  | 7.19 | 7.19 | 1 | 100 | 100
3 | WBM-I- 29.00 Km | 23.237km. |  | - | 23.237km. |  | 29 | 13.05 | 0.45 | 100 | 45
4 | WBM-II- 29.00 Km | - |  | - | - |  | 29 |  | 0 | 100 | 0
5 | WBM-III- 17.75 Km. | - |  | - | - |  | 17.75 |  | 0 | 100 | 0
6 | Black topping - 17.75 Km. | - |  | - | - |  | 17.75 |  | 0 | 100 | 0
7 | RCC Slab culvert (1 m span) 40.00 Nos. | 40Nos. |  | - | 40Nos. |  | 40 | 29 | 0.725 | 100 | 72.5
8 | RCC Slab culvert (2.00 m span) 4.00 Nos. | 4Nos. |  | - | 4Nos. |  | 4 | 4 | 1 | 100 | 100
9 | RCC Slab culvert (6.00 m span) 2.00 Nos. | 2Nos. |  | - | 2Nos. |  | 2 | 2 | 1 | 100 | 100
10 | R/wall (3.0 m ht) - 140.00 m | 80 mtr. |  | - | 80 mtr. |  | 140 |  | 0 | 100 | 0
11 | R/wall (4.0 m ht) - 60.00 m | 30 mtr. |  | - | 30 mtr. |  | 60 |  | 0 | 100 | 0
12 | B/wall ( 3.8 m ht) - 50.00 m | - |  | - | - |  | 50 |  | 0 | 100 | 0
13 | K/Drain - 29.00 Km. | 29.00km. |  | - | 29.00km. |  | 29 | 29 | 1 | 100 | 100
| Over all Physical Progress / Total expenditure | 60.56% |  |  |  | 1139.7 |  |  |  |  | 617.5
87%
| C. Progress Release of State share | [6 empty] | 87% |  |  | 88.2143
S/No. | Release of funds/payments | Date |  | Amount (Rs. in Lakhs) | Remarks
a. | Central Share |  |  | 989.7
b. | State Share | 2015-16 |  | 75
c. |  | 2016-17 |  | 75
| Total State Released : |  |  | 1139.7
| D. No. of Photographs attached :- | Nil
| Sd/- |  |  |  | Sd/-
| Executive Engineer, |  |  |  | Superintending Engineer,
| Kanubari P.W. Division. |  |  |  | Khonsa Circle, PWD, Khonsa
| Surveyor of Works | Sr. Finance & Accounts Officer, |  |  | Suptdg. Surveyor of Works O/o Chief Engineer (EZ), Itanagar , Arunachal Pradesh.
| O/o Chief Engineer (EZ), | O/o Chief Engineer (EZ) |  |  | O/o Chief Engineer (EZ)
| PWD, AP,Itanagar. | PWD, AP,Itanagar. |  |  | PWD, AP,Itanagar.
Signature by the Chief Engineer of Implementing Department
| Name : | Kenjom Ete
| Designation : | Chief Engineer, Eastern Zone, PWD, AP, Itanagar
Date :
| Place : | Itanagar
Office seal :

## Sumhak to Shalom
ANNEXURE - B
QUARTERLY PROGRESS REPORT FOR QUARTER ENDING SEPTEMBER-2017 PROJECT UNDER NON - LAPSABLE CENTRAL POOL OF RESOURCES SCHEME.
A. Indentification Particulars
1 | Name of Project | : | Construction of Road from Sumhak to Shalom via Upper Chinhan upto WBM level (14 Km) in Arunachal Pradesh.
2 | Location
| State | : | Arunachal Pradesh
| District | : | Tirap
3 | Approved cost (Rs. In lakh) | : | 1840.00 Lakhs
4 | Date of approval of Project/Scheme | : | 20/02/2014
5 | Tender cost (Rs. In lakhs) | : | 1836.25 Lakhs
6 | Date of award of contract (copy of work order to be attached (only once for the quarter in which it was issued) | : | 24/12/2014
7 | Whether contract awarded on Turn key basis | : | Yes
8 | Whether awarded work in being executed based on PERT/CPM | : | Yes
9 | Original Date of Completion of Project / Scheme | : | 28/02/2017
10 | Re-Schedule Date of Completion of Project / Scheme | : | 30/06/2017
11 | Executing Agency State Govt./ PSC/ Other agency (specify) | : | Arunachal Pradesh PWD
B. Over all Progress
S/No. | Item | Physical Progress (%) |  |  |  | Total Expenditure incurred (Rs. in lakh
|  | Beginning of Quarter |  | During Quarter | End of Quarter (Cummulative)
1 | 2 | 3 |  | 4 | 5 | C/S=1322.10 S/S= 132.24
1. | Jungle Clearance (13.88 Km) | 13.880 Km |  | - | 13.880 Km |  | QPR compiled from UC
2 | Formation Cutting (13.88 Km) | 13.880 Km |  | - | 13.880 Km
3 | Pavement:-
| a. GSB-I- 13.88 Km | 12.000 Km |  | 1.880 Km | 13.880 Km
| b. WBM-II-13.88 Km. | 9.000 Km |  | 4.880 Km | 13.880 Km
4 | CD works:-
| a. RCC Slab Culvert (2m)-45 Nos. | 41 Nos. |  | 6 Nos. | 47 Nos.
| a. RCC Slab Culvert (4m)-7 Nos. | 4 Nos. |  | - | 4 Nos.
| a. RCC Slab Culvert (6m)- 1 No. | - |  | - | -
5 | Protection Works:-
| a. Retaining & Breast Wall (3 Mtr) -700.00 mtr. | 550 mtr. |  | - | 550 mtr.
6 | Drainage:-
| a. Kutcha Drain- 13880.00 mtr. | 13880 mtr. |  | - | 13880 mtr.
| b. Pucca Drain- 4164.00 mtr. | 2000 mtr. |  | 2164 mtr. | 4164 mtr.
7 | Km Stone & Sign Board- 1 Job | - |  | - | -
| Over all Physical Progress / Total expenditure |  |  |  | 99% | 1454.34
C. Progress Release of State share
S/No. | Release of funds/payments | Date |  | Amount (Rs. in Lakhs) | Remarks
a | Central share |  |  | 1322.1
b | State Share |  |  | 132.24
| Total Fund Release : | - |  | 1454.34 | -
| D. No. of Photographs attached :- | Nil
| Sd/- |  |  |  | Sd/-
| Executive Engineer, |  |  |  | Superintending Engineer,
| Khonsa P.W. Division. |  |  |  | Khonsa Circle, PWD, Khonsa
| Surveyor of Works | Sr. Finance & Accounts Officer, |  |  | Suptdg. Surveyor of Works O/o Chief Engineer (EZ), Itanagar , Arunachal Pradesh.
| O/o Chief Engineer (EZ), | O/o Chief Engineer (EZ) |  |  | O/o Chief Engineer (EZ)
| PWD, AP,Itanagar. | PWD, AP,Itanagar. |  |  | PWD, AP,Itanagar.
Signature by the Chief Engineer of Implementing Department
| Name : | Kenjom Ete
| Designation : | Chief Engineer, Eastern Zone, PWD, AP, Itanagar
Date :
| Place : | Itanagar
Office seal :

## vkv- ldg
ANNEXURE - B
QUARTERLY PROGRESS REPORT FOR QUARTER ENDING SEPTEMBER-2017 PROJECT UNDER NON - LAPSABLE CENTRAL POOL OF RESOURCES SCHEME.
A. Indentification Particulars
1 | Name of Project | : | Establishment of V.K.V residential school at Longding in Longding District.
2 | Location
| State | : | Arunachal Pradesh
| District | : | Longding.
3 | Approved cost (Rs. In lakh) | : | Rs 897.19 Lakhs
4 | Date of approval of Project/Scheme | : | Dtd 30/01/2014
5 | Tender cost (Rs. In lakhs) | : | Rs. 804.76 Lakhs.
6 | Date of award of contract (copy of work order to be attached (only once for the quarter in which it was issued) | : | 30/10/2014 NA.
7 | Whether contract awarded on Turn key basis | : | NO
8 | Whether awarded work in being executed based on PERT/CPM | : | Yes
9 | Original Date of Completion of Project / Scheme | : | 27/11/2016
10 | Re-Schedule Date of Completion of Project / Scheme | : | NA.
11 | Executing Agency State Govt./ PSC/ Other agency (specify) | : | Arunachal Pradesh PWD
B. Over all Progress
S/No. | Item | Physical Progress (%) |  |  |  | Total Expenditure incurred (Rs. in lakh
|  | Beginning of Quarter |  | During Quarter | End of Quarter (Cummulative)
1 | 2 | 3 |  | 4 | 5 | 6
1 | School Building
i | School Building-1883 Sqm | Building completed except finishing |  | Minor work | Building completed except some minor work | C/S=579.43 S/S=32.30
ii | Hostel Building-1181.28 Sqm | Ground floor slab casting completed |  | - | Ground floor slab casting completed & First floor column work in progress
2 | Residential Building
i | T-I-8 Nos.-333.60 Sqm | Completed except finishing work |  | - | Completed except finishing work
ii | T-II-8 Nos.-407.08 Sqm | Completed except finishing work |  | - | Completed except finishing work
iii | T-III-4 Nos.-247.52 Sqm | Completed except finishing work |  | - | Completed
iv | T-IV-1 No.-90.22 Sqm | Site Dev. |  | - | Site Dev.
| Over all Physical Progress / Total expenditure |  |  |  | 88% | 611.73
C. Progress Release of State share
S/No. | Release of funds/payments | Date |  | Amount (Rs. in Lakhs) | Remarks
a | Central share |  |  | 579.43
b | State Share |  |  | 32.3
| Total Fund Release : | - |  | 611.73 | -
| D. No. of Photographs attached :- | Nil
| Sd/- |  |  |  | Sd/-
| Executive Engineer, |  |  |  | Superintending Engineer,
| Longding P.W. Division. |  |  |  | Khonsa Circle, PWD, Khonsa
| Surveyor of Works | Sr. Finance & Accounts Officer, |  |  | Suptdg. Surveyor of Works O/o Chief Engineer (EZ), Itanagar , Arunachal Pradesh.
| O/o Chief Engineer (EZ), | O/o Chief Engineer (EZ) |  |  | O/o Chief Engineer (EZ)
| PWD, AP,Itanagar. | PWD, AP,Itanagar. |  |  | PWD, AP,Itanagar.
Signature by the Chief Engineer of Implementing Department
| Name : | Kenjom Ete
| Designation : | Chief Engineer, Eastern Zone, PWD, AP, Itanagar
Date :
| Place : | Itanagar
Office seal :

## Multi Sport Complex at Namsai
ANNEXURE - B
QUARTERLY PROGRESS REPORT FOR QUARTER ENDING SEPTEMBER-2017 PROJECT UNDER NON - LAPSABLE CENTRAL POOL OF RESOURCES SCHEME.
A. Indentification Particulars
1 | Name of Project | : | Construction of Indoor Multi Sport Complex at Nmsai in Arunachal Pradesh
2 | Location
| State | : | Arunachal Pradesh
| District | : | Namsai
3 | Approved cost (Rs. In lakh) | : | 312.98 Lakhs (DNER/NLP/AP/205/2013 Dt. 29/12/2014)
4 | Date of approval of Project/Scheme | : | 27/06/2011
5 | Tender cost (Rs. In lakhs) | : | Rs.
6 | Date of award of contract [copy of work order to be attached (only once for the quarter in which it was issued) need not be submitted if submitted in earlier quarter) | :
7 | Whether contract awarded on Turn key basis | : | No, on item rate contract.
8 | Whether awarded work in being executed based on PERT/CPM | : | Yes
9 | Original Date of Completion of Project / Scheme | :
10 | Re-Schedule Date of Completion of Project / Scheme | :
11 | Executing Agency State Govt./ PSC/ Other agency (specify) | : | Arunachal Pradesh PWD
B. Over all Progress
S/No. | Item | Physical Progress (%) |  |  |  | Total Expenditure incurred (Rs. in lakh
|  | Beginning of Quarter |  | During Quarter | End of Quarter (Cummulative)
1 | 2 | 3 |  | 4 | 5 | 6
1. | Indoor Multisports complex Plinth area-1385.00 Sqm |  |  | Tender awarded | Tender awarded
Over all Physical Progress / Total expenditure
C. Progress Release of State share
S/No. | Release of funds/payments | Date |  | Amount (Rs. in Lakhs) | Remarks
a. | Central Share | 15.01.2015 |  | 112.67
B. | State Share |  |  | 13
| Total Fund Released : |  |  | 125.67
| D. No. of Photographs attached :- | Nil
| Sd/- |  |  |  | Sd/-
| Executive Engineer, |  |  |  | Superintending Engineer,
| Namsai P.W. Division. |  |  |  | Tezu Circle, PWD, Tezu
| Surveyor of Works | Sr. Finance & Accounts Officer, |  |  | Suptdg. Surveyor of Works O/o Chief Engineer (EZ), Itanagar , Arunachal Pradesh.
| O/o Chief Engineer (EZ), | O/o Chief Engineer (EZ) |  |  | O/o Chief Engineer (EZ)
| PWD, AP,Itanagar. | PWD, AP,Itanagar. |  |  | PWD, AP,Itanagar.
Signature by the Chief Engineer of Implementing Department
| Name : | Kenjom Ete
| Designation : | Chief Engineer, Eastern Zone, PWD, AP, Itanagar
Date :
| Place : | Itanagar
Office seal :